RWS 290—Business Writing and Rhetoric

Progress Memo Description

# Overview

For this assignment, your group will write a brief 1 page memo updating me on your progress for the recommendation report project.

Frequently, clients ask consultants to provide updates about their movement through a scope of work. These updates often take the form of a periodic or monthly progress report. Even in a tight project like the report, this memo allows me to place your group in the lifecycle of the project timeline, identify and correct any potential slippages, and help you anticipate future work.

Your group must be absolutely truthful about your progress as of deadline; include work you will do right up until that date. I’ll be reviewing these immediately after you submit them, and meet with your group individually soon after you submit the memo.

# Purpose and Context of the Memo

The best periodic reports account for how an audience could potentially retrieve (or read) the information about your progress. When they get your memo, your readers should be able to:

- Understand immediately where you are in the report project’s timeline;

- Learn more about your activities in a narrative, should they require it;

- Determine what each member has done so far, what each member is doing now, and what each member will do next; and,

- Verify what tasks the group will work on in the immediate future.

The memo should contain four sections. The General Activities section allows the reader to skim over a list of accomplishments quickly, while the Overview section presents amplified activities in a more developed narrative format of one short paragraph. Team members’ past work is outlined in the Individual Activities section, and the memo projects future work in the Forecast section, again, with individual responsibilities listed briefly.

Audience

I am the memo’s primary audience. I have some knowledge of your group’s report, but would like to have as much additional information about your movement forward as possible.

Format

Format the memo using the memo template on Canvas. Assume that your clients will want you to mirror this format; you must use Microsoft Word and follow the template exactly. Make sure all text is black.

Due

See schedule